## Project timeline
Project timeline
Project Milestones
Data | Milestone | Assigned to | Position | Baseline | Project Timeline Tip
2019-10-23 | 23.10 Workshop para descoberta do ambiente |  | 10 | 0 | Use the Position field in the Project milestones table to place the milestone labels where you want! Use positive numbers to position them above the timeline and negative numbers to position them below.
2019-11-08 | 09.11 Infra Build (deploy e configuração de ferramentas) |  | 5 | 0
2019-11-13 | 13.11 Entrega da visão geral de investimentos e custos |  | 20 | 0
2019-11-18 | 18.11 Fim do Assessment e Análise Técnica |  | 10 | 0
2019-11-27 | 27.11 Apresentação dos resultados do Cloud Advisory |  | 15 | 0
2019-12-15 | 15.12 Apontamento do parceiro para jornada Cloud |  | 5 | 0
|  |  | -10 | 0
0
0
0
0
0
0